Federation of Osborne and Featherstone Nursery Schools

Climate Action Plan

2025-2027

- Decarbonisation

| Baseline Assessment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Osborne Nursery School - Modern boiler installed via Salix Funding - LED lights throughout building with sensor activation - Some plastic strip doorway coverings to reduce heat loss from classrooms during free-flow time - Gas, electricity and water readings taken each month to assess and control usage - Bike / scooter / pushchair stores to encourage parents to walk their children to nursery - Removed the electric heaters from the café area and added it into the central heating system |  | Featherstone Nursery School - LED lights in nursery school half of building with sensor activation - Some plastic strip doorway coverings to reduce heat loss from classrooms during free-flow time - Bike / scooter / pushchair stores to encourage parents to walk their children to nursery |  |  |  |  |
| Aim / Objective | Action |  | School | Timeframe | ONS Staff Responsible | FNS Staff Responsible |
| To reduce the school’s carbon footprint by becoming more energy efficient. | Energy efficient LED lights installed in children centre half of Featherstone building BSS to monitor the energy usage monthly on the Featherstone school site. Update Featherstone’s main boilers to a more modern and energy efficient model. Ensure that the schools are only heated during cold weather and that heating is not left on when windows/doors are open. Install plug timers on suitable electricals (e.g. ipad charging case) Staff encouraged to switch off devices when not in use e.g. computers |  | FNS FNS FNS Both Both Both | July 2027 Dec 2025 July 2027 On-going Dec 25 Sep 25 | Tram Nguyen Tram Nguyen Sharon Eeles | Rachel Allen Zakia Parveen Rachel Allen Zakia Parveen Zakia Parveen Sharon Eeles |
| For staff to investigate alternative forms of transport. | Staff will be encouraged to use public transport, as both schools are located on a train route and several bus routes, where possible. Staff will also be encouraged to walk or cycle to work, where possible. |  | Both | On-going | Sharon Eeles | Sharon Eeles |
| To encourage children to cycle to nursery | Additional balance bikes purchased for the balance bike loan scheme to encourage children to ride a bike |  | Both | July 25 | Amy Rogerson | Amy Rogerson |
| To reduce the school’s carbon footprint by using local suppliers | Audit the companies where we source our resources from and begin to use a greater number of companies who are sustainable being mindful of companies who Greenwash. Greenwashing includes: Use of vague terms such as “eco-conscious” and “natural” to describe their products; green images such as mountains and plants on packaging; making one feature of their product eco-friendly when the rest of their range is damaging to nature; and even, making false claims such as that they use recyclable or biodegradable packaging even if they don’t. |  | Both | July 26 | Sarrina Stephens | Rachel Allen |
| To reduce the amount of food waste in our local community. | To use the FareShare community app to source excess food from supermarkets to supplement the school snack and to support families in need. |  | Both | July 27 | Sharon Eeles | Sharon Eeles |
| To reduce heat loss from heated rooms in winter | To install additional plastic strip doorway coverings to reduce heat loss from classrooms and corridors during free-flow time |  | Both | Oct 25 | Tram Nguyen | Zakia Parveen |

- Biodiversity

| Baseline Assessment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Osborne Nursery School - Large garden area with flowerbeds, grassed terraces and a sensory area - Natural area on site where Forest School activities take place - Received funding from National Education Nature Park in 2024 & 2025 for Grey to Green project to increase biodiversity - Bug hotel in Forest School |  | Featherstone Nursery School - Large field area and garden area with pots and planters - Natural area on site where Forest School activities take place - Received funding from National Education Nature Park in 2024 & 2025 for Grey to Green project to increase biodiversity - Wildflower area created in corner of playground - Creation of the bog garden has increased variety of plants on site |  |  |  |  |
| Aim / Objective | Action |  | School | Timeframe | ONS Staff Responsible | FNS Staff Responsible |
| To create a range of habitats on the school site for the children to explore. | A bug hotel will be developed in Featherstone’s Forest School to increase biodiversity in this area. The wildlife corner in the playground at Featherstone will be developed to increase biodiversity in this area. Wildflowers to be added to grass terraces at Osborne Fruit trees to be added on field / grass terraces Planting areas & hanging baskets to be developed in both Little Learner garden areas |  | FNS FNS ONS Both Both | Dec 25 July 25 July 26 Mar 25 Dec 25 | Denise Hughes Julie Attwood Danielle Warner | Lindsey Miles Jackie Fortey Jackie Fortey Shervorne Richardson |

- Adaptation and Resilience

| Baseline Assessment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Osborne Nursery School - Plastic strip doorway coverings removed during Summer Term to increase ventilation and air flow in classrooms - Opening skylights installed in classrooms and staffroom to increase ventilation in warmer months - Blinds installed on classroom and office windows to prevent rooms overheating in hot weather - Large trees provide shade in summer months in garden - Sunhats provided for children to protect from sun - Windows and doors in all classrooms used to increase ventilation and through air in hot weather - Canopies enable children to access the outside learning spaces in all weathers & provide shade to some rooms |  | Featherstone Nursery School - Plastic strip doorway coverings removed during Summer Term to increase ventilation and air flow in classrooms - Bog garden created to take excess rainwater off the playground to enable the area to be used all year round - Blinds installed on classroom and office windows to prevent rooms overheating in hot weather - Sail installed on field to provide shade in summer months - Sunhats provided for children to protect from sun - Windows and doors in all classrooms used to increase ventilation and through air in hot weather - Canopies enable children to access the outside learning spaces in all weathers & provide shade to some rooms |  |  |  |  |
| Aim / Objective | Action |  | School | Timeframe | ONS Staff Responsible | FNS Staff Responsible |
| To ensure the learning spaces are kept at a temperature conducive to learning | Investigate ways to reduce the temperature in Little Learners outdoor space on hot days Investigate ways to reduce the temperature in Cherry Room on hot days e.g. could solar control window film be added? |  | ONS FNS | July 27 July 27 | Sharon Eeles | Sharon Eeles |

- Climate Education and Green Careers

| Baseline Assessment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Osborne Nursery School - Forest School activities for all children embedded in our curriculum - Growing activities are included in our curriculum - Some sustainability topics are covered through our Rights Respecting work with the children |  | Featherstone Nursery School - All 3-4 year olds have fortnightly Forest School sessions - Growing activities are included in our curriculum - Some sustainability topics are covered through our Rights Respecting work with the children |  |  |  |  |
| Aim / Objective | Action |  | School | Timeframe | ONS Staff Responsible | FNS Staff Responsible |
| For staff to feel confident when teaching children about the natural environment and climate change | Teaching staff to use the materials and activities from the National Education Nature Park to enhance learning opportunities. Staff training on new recycling laws & how these have been implemented at Featherstone Nursery School Additional picture books to be purchased to simply explain / introduce climate education themes Adjust curriculum plan so sustainability is more explicitly taught |  | Both Both Both Both | On-going Mar 25 Dec 25 July 26 | Liz Jones Sharon Eeles Amy Rogerson Amy Rogerson | Jackie Fortey / Lindsey Miles Sharon Eeles Amy Rogerson Amy Rogerson |
| For children to have access to the outdoor areas all year round. | To re-waterproof / replace as needed the wet weather clothing to enable children to access outdoor learning throughout the year Continue to develop the bog area at Featherstone that drains the standing water off the playground To develop further the outdoor learning spaces by auditing the resources we have and purchasing others to make the spaces more purposeful. Also by clearing the natural spaces of unused items. |  | Both FNS Both | On-going July 25 Oct 25 | Forest School Leaders Amy Rogerson | Forest School Leaders Jackie Fortey Amy Rogerson |
| For children to learn about the natural environment and climate change | The topics/areas that we teach the children related to sustainability will be included in our curriculum plans. Children will be taught about the weather and also the importance they can play in looking after their environment e.g. turning off lights/taps, recycling and picking up litter etc. Continue to develop fortnightly forest school sessions for Explorers at Featherstone to embed it into our curriculum Introduce Forest School for Little Learners at Featherstone to enable our youngest children to begin to learn about caring for our nursery environment |  | Both FNS FNS | July 26 July 25 July 25 | Amy Rogerson | Amy Rogerson Lindsey Miles Mariyah Fiaz |
| For children to grow their own fruit and vegetables for use in nursery so they understand where food comes from | New fruit trees will be planted around the school site and the fruit picked and eaten by the children Children will also grow their own vegetables in the allotment areas New gardening equipment will be purchased (using Garden grant money) to ensure that children can be taught gardening skills each year. Herb areas developed with the herbs being used in cooking activities |  | Both Both Both Both | Nov 25 On-going Mar 25 July 25 | Amy Rogerson Keyworkers Amy Rogerson Danielle Warner | Jackie Fortey Keyworkers Jackie Fortey Shervorne Richardson |
| For children to understand the impact they can have on climate change | Introduce the relevant Sustainability Hero to the children as sustainability topics are raised through our curriculum Climate Action Superheroes - United Nations Sustainable Development |  | Both | From Sept 26 | Liz Jones | Jackie Fortey / Lindsey Miles |

- Sustainable Use of Resources

| Baseline Assessment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Osborne Nursery School - ‘Waste’ products used in learning activities with children e.g. box construction, bottle tops for counting etc. - Water butts installed to collect rainwater for watering plants - Paper recycling embedded - Sensor taps in children’s toilets reduce water usage - Drinking water machine uses tap water |  | Featherstone Nursery School - ‘Waste’ products used in learning activities with children e.g. box construction, bottle tops for counting etc. - Water butts installed to collect rainwater for watering plants - Paper recycling embedded - Push taps in children’s toilets reduce water usage - Multi-use cups used for children’s drinking water - Drinking water machine uses tap water - Bog garden created on playground (using NENP money) to naturally drain water off playground to water the plants there |  |  |  |  |
| Aim / Objective | Action |  | School | Timeframe | ONS Staff Responsible | FNS Staff Responsible |
| To conserve water | Leaking taps and toilets will be repaired as soon as possible to prevent water being wasted. Install Hippo Bricks or Buffalloo Bags in cisterns to reduce water |  | Both | On-going | Tram Nguyen | Zakia Parveen |
| Reduce clothes going into landfill | Set up clothing swap racks for parents to donate and receive unused clothes from |  | Both | July 26 | Sharon Eeles | Sharon Eeles |
| Composting of raw fruit, veg and toilet rolls | Children and staff actively using compost bins to depose of compostable waste |  | Both | Dec 25 | Sharon Eeles | Sharon Eeles |
| Maximize recycling of resources | Staff trained on new recycling requirements Additional mixed recycling and food waste bins purchased for classrooms and staff areas of the schools Zero landfill waste disposal company sourced Children taught about recycling as part of the curriculum and actively encouraged to use the recycling bins around school Additional picture books purchased which simply explain recycling Add recycling information to parents information on website, newsletters and Tapestry notices |  | All Both | Mar 25 Apr 25 May 25 From Sep 25 July 25 Dec 25 | Sharon Eeles Sarrina Stephens Liz Jones Amy Rogerson SLT | Sharon Eeles Rachel Allen Jackie Fortey/Lindsey Miles Amy Rogerson SLT |
| Reduce single plastic use | Purchase reusable cups for children’s drinking water machine |  | ONS | Dec 25 | Sharon Eeles |  |
| Reduce the use of paper and printing | Ensure the majority of messages and handouts are sent electronically to parents |  | Both | On-going | Amy Rogerson | Amy Rogerson |